## GanttChart
Gantt Chart					© 2008 Vertex42 LLC	0
				Download Professional Version for Excel
[Project Name]
[Company Name]

	Project Lead:	Mike LoVerme
	Due Date:	5/5/2010	(Wed)	(vertical red line)
[42]	Start Date:	1/19/2010	(Tue)					First Day of Week (Sun=1):	2	1/18/2010	1/19/2010	1/20/2010	1/21/2010	1/22/2010	1/23/2010	1/24/2010	1/25/2010	1/26/2010	1/27/2010	1/28/2010	1/29/2010	1/30/2010	1/31/2010	2/1/2010	2/2/2010	2/3/2010	2/4/2010	2/5/2010	2/6/2010	2/7/2010	2/8/2010	2/9/2010	2/10/2010	2/11/2010	2/12/2010	2/13/2010	2/14/2010	2/15/2010	2/16/2010	2/17/2010	2/18/2010	2/19/2010	2/20/2010	2/21/2010	2/22/2010	2/23/2010	2/24/2010	2/25/2010	2/26/2010	2/27/2010	2/28/2010	3/1/2010	3/2/2010	3/3/2010	3/4/2010	3/5/2010	3/6/2010	3/7/2010	3/8/2010	3/9/2010	3/10/2010	3/11/2010	3/12/2010	3/13/2010	3/14/2010	3/15/2010	3/16/2010	3/17/2010	3/18/2010	3/19/2010	3/20/2010	3/21/2010	3/22/2010	3/23/2010	3/24/2010	3/25/2010	3/26/2010	3/27/2010	3/28/2010	3/29/2010	3/30/2010	3/31/2010	4/1/2010	4/2/2010	4/3/2010	4/4/2010	4/5/2010	4/6/2010	4/7/2010	4/8/2010	4/9/2010	4/10/2010	4/11/2010	4/12/2010	4/13/2010	4/14/2010	4/15/2010	4/16/2010	4/17/2010	4/18/2010	4/19/2010	4/20/2010	4/21/2010	4/22/2010	4/23/2010	4/24/2010	4/25/2010	4/26/2010	4/27/2010	4/28/2010	4/29/2010	4/30/2010	5/1/2010	5/2/2010	5/3/2010	5/4/2010	5/5/2010	5/6/2010	5/7/2010	5/8/2010	5/9/2010	5/10/2010	5/11/2010	5/12/2010	5/13/2010	5/14/2010	5/15/2010	5/16/2010	5/17/2010	5/18/2010	5/19/2010	5/20/2010	5/21/2010	5/22/2010	5/23/2010	5/24/2010	5/25/2010	5/26/2010	5/27/2010	5/28/2010	5/29/2010	5/30/2010	5/31/2010	6/1/2010	6/2/2010	6/3/2010	6/4/2010	6/5/2010	6/6/2010	6/7/2010	6/8/2010	6/9/2010	6/10/2010	6/11/2010	6/12/2010	6/13/2010	6/14/2010	6/15/2010	6/16/2010	6/17/2010	6/18/2010	6/19/2010	6/20/2010	6/21/2010	6/22/2010	6/23/2010	6/24/2010	6/25/2010	6/26/2010	6/27/2010	6/28/2010	6/29/2010	6/30/2010	7/1/2010	7/2/2010	7/3/2010	7/4/2010	7/5/2010	7/6/2010	7/7/2010	7/8/2010	7/9/2010	7/10/2010	7/11/2010	7/12/2010	7/13/2010	7/14/2010	7/15/2010	7/16/2010	7/17/2010	7/18/2010	7/19/2010	7/20/2010	7/21/2010	7/22/2010	7/23/2010	7/24/2010	7/25/2010	7/26/2010	7/27/2010	7/28/2010	7/29/2010	7/30/2010	7/31/2010	8/1/2010	8/2/2010	8/3/2010	8/4/2010	8/5/2010	8/6/2010	8/7/2010	8/8/2010	8/9/2010	8/10/2010	8/11/2010	8/12/2010	8/13/2010	8/14/2010	8/15/2010	8/16/2010	8/17/2010	8/18/2010	8/19/2010	8/20/2010	8/21/2010	8/22/2010	8/23/2010	8/24/2010	8/25/2010	8/26/2010	8/27/2010	8/28/2010	8/29/2010	8/30/2010	8/31/2010	9/1/2010	9/2/2010	9/3/2010	9/4/2010	9/5/2010	9/6/2010	9/7/2010	9/8/2010	9/9/2010	9/10/2010	9/11/2010	9/12/2010
WBS	Tasks	Task Lead	Start	End	Duration (Days)	% Complete	Working Days	Days Complete	Days Remaining		18 - Jan - 10					25 - Jan - 10					01 - Feb - 10					08 - Feb - 10					15 - Feb - 10					22 - Feb - 10					01 - Mar - 10					08 - Mar - 10					15 - Mar - 10					22 - Mar - 10					29 - Mar - 10					05 - Apr - 10					12 - Apr - 10					19 - Apr - 10					26 - Apr - 10					03 - May - 10					10 - May - 10					17 - May - 10					24 - May - 10					31 - May - 10					07 - Jun - 10					14 - Jun - 10					21 - Jun - 10					28 - Jun - 10					05 - Jul - 10					12 - Jul - 10					19 - Jul - 10					26 - Jul - 10					02 - Aug - 10					09 - Aug - 10					16 - Aug - 10					23 - Aug - 10					30 - Aug - 10					06 - Sep - 10

1	Task Category 1	Ryan	1/19/10	1/20/10	1	0%	2	0	1
1.1	Sub Task		1/19/10	1/20/10	1	0%	2	0	1
1.2	Sub Task		1/19/10	1/19/10	0	0%	1	0	0
1.3	Sub Task		1/19/10	1/19/10	0	0%	1	0	0
1.4	Sub Task		1/19/10	1/19/10	0	0%	1	0	0
2	Task Category 2	Jon	1/19/10	2/27/10	39	0%	29	0	39
2.1	Sub Task		1/19/10	2/05/10	17	0%	14	0	17
2.2	Sub Task		1/19/10	2/05/10	17	0%	14	0	17
2.3	Sub Task		1/19/10	2/27/10	39	0%	29	0	39
2.4	Sub Task		1/19/10	2/16/10	28	0%	21	0	28
3	Task Category 3	Tony	1/19/10	2/25/10	37	0%	28	0	37
3.1	Sub Task		1/19/10	2/05/10	17	0%	14	0	17
3.2	Sub Task		1/19/10	2/05/10	17	0%	14	0	17
3.3	Sub Task		1/19/10	2/25/10	37	0%	28	0	37
3.4	Sub Task		1/19/10	2/17/10	29	0%	22	0	29
3	Task Category 3	Bill	1/19/10	2/25/10	37	0%	28	0	37
3.1	Sub Task		1/19/10	2/05/10	17	0%	14	0	17
3.2	Sub Task		1/19/10	2/05/10	17	0%	14	0	17
3.3	Sub Task		1/19/10	2/25/10	37	0%	28	0	37
3.4	Sub Task		1/19/10	2/17/10	29	0%	22	0	29
3	Task Category 3	Bill	1/19/10	2/25/10	37	0%	28	0	37
3.1	Sub Task		1/19/10	2/05/10	17	0%	14	0	17
3.2	Sub Task		1/19/10	2/05/10	17	0%	14	0	17
3.3	Sub Task		1/19/10	2/25/10	37	0%	28	0	37
3.4	Sub Task		1/19/10	2/17/10	29	0%	22	0	29
3	Task Category 3	Bill	1/19/10	2/25/10	37	0%	28	0	37
3.1	Sub Task		1/19/10	2/05/10	17	0%	14	0	17
3.2	Sub Task		1/19/10	2/05/10	17	0%	14	0	17
3.3	Sub Task		1/19/10	2/25/10	37	0%	28	0	37
3.4	Sub Task		1/19/10	2/17/10	29	0%	22	0	29

HELP / - Modify the GREEN cells and the WBS, Tasks, and Task Lead columns. The rest of the columns are formulas. / - The number of weeks shown in the gantt chart is limited by the maximum number of columns available. / - The Start Date that you choose determines the first week in the gantt chart, starting on a Monday. / - Change the first day of the week via cell K8 / - Use the slider to adjust the range of dates shown in the gantt chart. / - Only 34 weeks can be shown/printed at one time, because each week uses up 7 columns. / Q: How do I make Task 2 start the day after the end of Task 1? / Use the following formula for the start date of Task 2: / =EndDate+1 / where EndDate is the reference to the cell containing the end date of task 1 / Q: How do I add/insert tasks and subtasks? / Copy the entire ROW (or a group of rows) for the type of task(s) you want to add and then right-click on the row where you want to insert the new tasks, then select Insert Copied Cells. / Important Note: When inserting a new subtask after the last subtask or before the first subtask, you will need to update the formulas for calculating the Level 1 %Complete and Duration (see below) to include the new subtask, because the ranges won't automatically expand to include the additional row. / Q: How do I calculate the %Complete for a Level 1 task based upon the %Complete of all of the associated subtasks? / Example: If Task 1 is on row 11 and the subtasks are on rows 12-15, use the following formula: / =SUMPRODUCT(F12:F15;G12:G15)/SUM(F12:F15) / Q: How do I calculate the Duration for a Level 1 task based upon the largest end date of a sub task? / Example: If the Level 1 task is on row 11 and the sub tasks are on rows 12-15, use the following formula / =MAX(E12:E15)-D11 / Q: How can I include holidays in the calculation of the Working Days? / You can add a list of holidays to exclude in the NETWORKDAYS function. See the help on that function. / Q: How do I change the print settings? / Select the entire range of cells that you want to print and then define a Print Range in the Format menu. Then go to Format > Page and select the Sheet tab. Adjust the Scaling mode as desired.